## Stakeholders
Stakeholder Identification | [5 empty] | Engagement Matrix | [5 empty] | Engagement Strategies |  |  | Communication Matrix
Stakeholders | Type | Role | Primary/ secondary | Influence | Interest | Unaware | Resistant | Netrual | Supporting | Leading | Action Plan | Engagement Strategies | Communication Plan | Frequency | Type of Information | Communication Channels | Frequency
International Defense Organizations (NATO) | Internal | Key | Primary | High | High |  |  |  | A (actual) | D (desired) | Conduct regular consultations and provide updates on operational developments. | Collaborate to align drone development with NATO's defense standards and strategies. | Joint training programs, Share non-sensitive data about the project’s progress | Monthly updates, Bi-annual programs | Compliance and progress updates | Video conferences, whitepaper (in-depth report) | Quarterly
Government Military Authorities | Internal | Key | Primary | High | High |  |  |  |  | A (actual) D (desired) | Continue detailed updates through monthly meetings and progress reports. | Maintain close collaboration and involve in decision-making processes | Formal reports, meetings, presentations | Monthly | Risk assessments, progress updates, final deliverables | Meetings, reports | Bi-weekly
Drone Operators | External | Key | Secondary | High | High |  |  |  | A (actual) D (desired) |  | Organize focused discussions and integrate feedback into drone functionality. | Gather operational feedback and ensure drones meet their needs | Focus groups, training workshops, feedback forms | Monthly | User manuals, quids | Webinars, emails | Bi-weekly
Testers | External | Project Team Member | Primary | High | Low |  |  | A(actual) | D (desired) |  | Implement continuous training programs and early involvement in drone testing | Provide continuous training and ensurex usability feedback | Training programs, user feedback sessions | Bi-monthly | Bug reports, test plans, and results | Testing software, task management tools | Weekly
Drone Software Engineers | Internal | Project Team Member | Primary | High | Low |  |  | A (actual) | D (desired) |  | Engage in daily standups and innovation sessions to enhance involvement. | Promote innovation and encourage participation in solution development | Daily standups, brainstorming sessions, progress reports | Daily/Weekly | Technical requirements, design iterations, testing results, and development progress | Agile tools, emails, meetings | Daily updates during sprints; weekly for overall progress
Factory Workers | Internal | Project Team Member | Primary | High | Low |  |  | A (actual) | D (desired) |  | Organize workshops for quality control and gather feedback to improve production. | Improve involvement in production and gather feedback | Feedback workshops, performance updates | Monthly | Production schedules, safety protocols, and quality updates | Notice boards, team meetings | Weekly
Drone Manufacturers (competitors) | Internal | External | Secondary | Low | High |  |  | A (actual) D (desired) |  |  | Monitor market trends and technology innovations; maintain competitive intelligence. | Monitor market trends and advancements | Trade shows, competitive analysis | Quarterly | None. Only monitor activities and address compliance risks | N/A | N/A
International Military Companies | External | External | Secondary | Low | High |  |  | A (actual) | D (desired) |  | Hold quarterly briefings to align expectations and build a strategic partnership. | Collaborate to align project goals with international standards | Strategy workshops, periodic consultations | Bi-annually or as needed | Collaboration updates, feature demonstrations, and security compliance | Webinars, presentations, formal emails | Monthly updates; as-needed during critical stages
Drone Piloting Schools | External | External | Secondary | Low | High |  |  | A (actual) | D (desired) |  | Collaborate on curriculum development and offer training access. | Collaborate on curriculum development and training | Joint planning sessions, feedback on training content | Bi-annually | Training materials and updates on drone systems | Workshops, webinars, email newsletters | Quarterly
Terrorist states | External | External | Secondary | Low | High | A (actual) D (desired) |  |  |  |  | Strengthen security protocols and prevent malicious drone use. | Prevent access to drones and reduce the risk of misuse | Strict regulations on drone exports, Incorporate technology | No direct communication | None. Only monitor activities and address compliance risks | N/A | N/A
Outlaws | External | External | Secondary | Low | High | A (actual) D (desired) |  |  |  |  | Strengthen security protocols and prevent malicious drone use. | Prevent malicious use and monitor threats | Sharing intelligence with law enforcement agencies | No direct communication | None—only monitor and report activities | N/A | N/A
Civilians in State-of-War Countries | External | Community | Secondary | Low | Low | A (actual) |  |  | D (desired) |  | Create public awearness programs to address privacy and safety concerns | Build trust through transparency and address safety concerns | Public outreach campaigns, Q&A sessions | As needed | Information on drone safety and operational transparency | Public announcements, media releases, websites | As-needed; before major deployments
Police Officers | External | Community | Secondary | Low | High | A (actual) |  |  | D (desired) |  | Conduct workshops to introduce drone usage for law enforcement applications. | Introduce drones for law enforcement operations | Awareness sessions, operational workshops | Quarterly | Operational training, system updates, and post-deployment feedback | Workshops, emails, on-site demonstrations | Bi-monthly updates: As needed for trainings
Security Guards | External | Community | Secondary | Low | High |  |  | A (actual) | D (desired) |  | Provide specialized training on drone-assisted security operations and gather feedback. | Train on drone-assisted operations | Specialized training sessions, operational feedback | Bi-monthly | Training on drone usage, maintenance updates, and operational feedback | Email newsletters, workshops | Bi-monthly updates: As needed for trainings
Business Who Support Military | External | Community | Secondary | High | High |  |  | A (actual) | D (desired) |  | Develop formal partnerships and hold regular business review sessions. | Engage in supply chain management and explore partnerships | Vendor meetings, joint reviews | Bi-monthly | Updates on project progress, supply chain needs, and technology improvements | Business briefings, email newsletters, and webinars | Bi-monthly

## Gantt
| ScatterSky |  |  |  |  | Project start: 2024-11-01
[6 empty] | 1 year | [47 empty] | 2 year
TASK ID | TASK | ASSIGNED TO | PROGRESS | START | END | 1 month |  |  |  | 2 month |  |  |  | 3 month |  |  |  | 4 month |  |  |  | 5 month |  |  |  | 6 month |  |  |  | 7 month |  |  |  | 8 month |  |  |  | 9 month |  |  |  | 10 month |  |  |  | 11 month |  |  |  | 12 month |  |  |  | 1 month |  |  |  | 2 month |  |  |  | 3 month |  |  |  | 4 month |  |  |  | 5 month |  |  |  | 6 month |  |  |  | 7 month |  |  |  | 8 month |  |  |  | 9 month |  |  |  | 10 month |  |  |  | 11 month |  |  |  | 12 month
TASK ID | [5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Project Initiation
1.1.1 | Define Project Scope | Project Manager | 100% | 2024-10-01 | 2024-10-08 | bar: 1 month 1
1.1.2 | Stakeholder Identification | Stakeholder Manager | 100% | 2024-10-04 | 2024-10-08 | bar: 1 month 1
1.1.3 | Develop Project Charter | Project Manager | 100% | 2024-10-07 | 2024-10-14 | bar: 1 month 2 to 1 month 3
M 1.2 | Project Charter Approved |  | Complete |  | 2024-10-15 | bar: 1 month 4
1.1.4 | Assemble Project Team | Project Manager | 100% | 2024-10-07 | 2024-10-14 | bar: 1 month 2 to 1 month 3
1.1.5 | Market Research | Business Analyst | 100% | 2024-10-07 | 2024-10-14 | bar: 1 month 2 to 1 month 3
1.1.6 | Risk managment Plan | Business Analyst | 100% | 2024-10-14 | 2024-10-17 | bar: 1 month 3
1.1.7 | Plan Budget | Financial Analyst | 100% | 2024-10-16 | 2024-10-18 | bar: 1 month 3
1.1.8 | Plan Schedule | Project Manager | 100% | 2024-11-25 | 2024-10-29 | bar: 1 month 4
M 1.1 | Project Kickoff |  | Complete |  | 2024-11-01 | bar: 2 month 1
Requirements and Planning
1.2.1 | Sofware Requirements Srecification | Requirements Analyst | 100% | 2024-10-30 | 2024-11-13 | bar: 1 month 4 to 2 month 1
1.2.2 | Hardware Requirements Specification | Requirements Analyst | 100% | 2024-11-06 | 2024-11-20 | bar: 2 month 1 to 2 month 2
M 2.1 | Requirements Document Approved |  | Complete |  | 2024-11-21 | bar: 2 month 2
1.2.3.1 | Identify Regulatory Standards | System Architect | 100% | 2024-11-06 | 2024-11-08 | bar: 2 month 1
1.2.3.2 | Gap Analysis | System Architect | 100% | 2024-11-20 | 2024-11-25 | bar: 2 month 3
1.2.4.1 | Blueprints | Hardware Engineers | 100% | 2024-11-20 | 2024-12-03 | bar: 2 month 3 to 2 month 4
M 2.2 | Blueprint and design approved |  | Complete |  | 2024-12-04 | bar: 3 month 1
1.2.4.2 | Prototype Validation | Hardware Engineers | 100% | 2024-12-04 | 2024-12-08 | bar: 3 month 1
1.2.4.3 | Software Algorithm Design | UI/UX Designer | 100% | 2024-12-04 | 2024-12-11 | bar: 3 month 1
M 2.3 | System Architecture Finalized |  | Complete |  | 2024-12-12 | bar: 3 month 2
Software Development
1.3.1.1 | Autonomous Navigation Algorithms | AI Engineer | 25% | 2024-12-11 | 2025-01-01 | bar: 3 month 2 to 3 month 4
1.3.1.2 | Obstacle Detection and Avoidance | AI Engineer | 0% | 2024-12-18 | 2025-01-08 | bar: 3 month 3 to 4 month 1
1.3.1.3 | Communication Systems Development | Systems Developer | 50% | 2024-12-11 | 2024-12-26 | bar: 3 month 3 to 3 month 4
1.3.1.4 | Develop Real-time Communication Protocols | Cybersecurity Specialist | 25% | 2024-12-12 | 2024-12-26 | bar: 3 month 3 to 3 month 4
1.3.1.5 | UI/UX Design | Software Developer | 25% | 2024-12-15 | 2024-12-22 | bar: 3 month 3 to 3 month 4
1.3.1.6 | Implement Security Measures Against Hacking | Cybersecurity Specialist | 50% | 2024-12-15 | 2024-12-29 | bar: 3 month 3 to 3 month 4
1.3.1.7 | Data Encryption for Communication | Cybersecurity Specialist | 0% | 2024-12-30 | 2025-01-06 | bar: 3 month 4 to 4 month 1
M 3.1 | Software Development Complete |  | On Track |  | 2024-12-27 | bar: 4 month 1
1.3.2.1 | Code Reviews and Debugging | Software Developer | 0% | 2025-01-07 | 2025-01-21 | bar: 4 month 2 to 4 month 3
1.3.2.2 | Version Control and Documentation | Software Developer | 0% | 2025-01-21 | 2025-01-28 | bar: 4 month 4
M 3.2 | Quality assurance of the software |  | Scheduled |  | 2025-01-29 | bar: 4 month 4
Hardware Development
1.4.1 | Build Initial Drone Body Prototype | Prototyping Technician | 25% | 2024-12-09 | 2025-01-15 | bar: 3 month 2 to 4 month 3
M 4.1 | Hardware Prototype Ready |  | On Track |  | 2025-01-16 | bar: 4 month 3
1.4.2 | Hardware Component Testing | Prototyping Technician | 0% | 2025-01-08 | 2025-02-10 | bar: 4 month 3 to 5 month 2
1.4.3 | Integrate Sensors, Cameras and Actuators | Hardware Engineer | 0% | 2025-02-11 | 2025-03-20 | bar: 5 month 3 to 6 month 3
1.4.4 | Evaluate Battery Life and Power Consuption | Hardware Engineer | 0% | 2025-02-11 | 2025-03-04 | bar: 5 month 3 to 6 month 1
M 4.2 | Functionality Evaluated |  | Scheduled |  | 2025-03-21 | bar: 6 month 3
1.4.5.1 | Refine Aerodynamic Design | Sensor Specialist | 0% | 2025-03-17 | 2025-03-24 | bar: 6 month 3 to 6 month 4
1.4.5.2 | Optimize Weight for Maximum Efficiency | Hardware Engineer | 0% | 2025-03-17 | 2025-03-24 | bar: 6 month 3 to 6 month 4
M 4.3 | Perfomance Optimized |  | Scheduled |  | 2025-03-25 | bar: 6 month 4
Testing
1.5.1.1 | Test Individual Software Modules | Flight Test Engineer | 0% | 2025-03-24 | 2025-04-09 | bar: 6 month 4 to 7 month 2
1.5.1.2 | Verify Hardware Components | Test Engineer | 0% | 2025-02-11 | 2025-02-21 | bar: 5 month 3 to 5 month 4
M 5.1 | Unit Testing Complete |  | Scheduled |  | 2025-04-10 | bar: 7 month 2
1.5.2 | Integration Testing | Test Engineer | 0% | 2025-03-24 | 2025-04-16 | bar: 6 month 4 to 7 month 3
M 5.2 | Integration Testing Complete |  | Scheduled |  | 2025-04-17 | bar: 7 month 3
1.5.3 | Performance Testing | Flight Test Engineer | 0% | 2025-03-24 | 2025-04-16 | bar: 6 month 4 to 7 month 3
M 5.3 | Performance Testing Complete |  | Scheduled |  | 2025-04-17 | bar: 7 month 3
1.5.4 | Security Testing | Test Engineer | 0% | 2025-03-24 | 2025-04-25 | bar: 6 month 4 to 7 month 3
M 5.4 | Security Testing Complete |  | Scheduled |  | 2025-04-17 | bar: 7 month 3
M 5.5 | Testing Complete |  | Scheduled |  | 2025-04-21 | bar: 7 month 4
Manufacturing
1.6.1.1 | Source Required Materials and Components | Supply Chain Manager | 0% | 2025-02-24 | 2025-03-12 | bar: 6 month 1 to 6 month 3
1.6.1.2 | Verify Supplier Quality Standards | Supply Chain Manager | 0% | 2025-03-10 | 2025-03-13 | bar: 6 month 3
1.6.2.1 | Establish Manufacturing Lines | Factory Supervisor | 0% | 2025-03-24 | 2025-04-07 | bar: 6 month 4 to 7 month 1
M 6.1 | Manufacturing Workflow Established |  | Scheduled |  | 2025-04-08 | bar: 7 month 1
1.6.2.2 | Educate Factory Workers on Assembly Procedures | Factory Supervisor | 0% | 2025-03-24 | 2025-04-25 | bar: 6 month 4 to 7 month 3
M 6.2 | Completion of education |  | Scheduled |  | 2025-04-28 | bar: 7 month 3
1.6.3.1 | Assemble Drone Bodies | Manufacturing Engineer | 0% | 2025-04-28 | 2025-05-19 | bar: 7 month 4 to 8 month 2
1.6.3.2 | Assemble Drone Remote Controls | Manufacturing Engineer | 0% | 2025-05-12 | 2025-05-19 | bar: 8 month 2 to 8 month 3
1.6.3.3 | Install Software and Hardware Components | Manufacturing Engineer | 0% | 2025-05-26 | 2025-06-02 | bar: 8 month 4
1.6.4 | Approve Units for Deployment | Quality Assurance Specialist | 0% | 2025-06-03 | 2025-06-24 | bar: 9 month 1 to 9 month 3
M 6.3 | Manufacture Complete |  | Scheduled |  | 2025-06-25 | bar: 9 month 4
Deployment
1.7.1.1 | Define Deployment Strategy | Deployment Engineer | 0% | 2025-06-30 | 2025-07-07 | bar: 9 month 4
1.7.1.2 | Allocate Deployment Resources | Deployment Engineer | 0% | 2025-07-08 | 2025-07-22 | bar: 10 month 1 to 10 month 2
M 7.1 | Deployment Plan Finalized |  | Scheduled |  | 2025-07-23 | bar: 10 month 2
1.7.2 | Install Final Software and Hardware | Deployment Engineer | 0% | 2025-07-08 | 2025-07-22 | bar: 10 month 1 to 10 month 2
1.7.3 | Prepare Maintenance and Support Manuals | IT Support Specialist | 0% | 2025-06-30 | 2025-07-14 | bar: 9 month 4 to 10 month 1
M 7.2 | Manuals and guides prepared |  | Scheduled |  | 2025-07-15 | bar: 10 month 2
1.7.4 | Open Drones for Sale | Logistics Coordinator | 0% | 2025-07-28 | 2025-08-11 | bar: 10 month 3 to 10 month 4
M 7.3 | System Deployed to End Users |  | Scheduled |  | 2025-08-12 | bar: 11 month 1
Post-deployment
1.8.1 | Schedule Regular Maintenance | Support Technician | 0% | 2025-08-11 | 2025-08-18 | bar: 11 month 1
M 8.1 | Continuous Improvement Plan Established |  | Scheduled |  | 2025-08-19 | bar: 11 month 2
1.8.2 | Collect User Feedback | Support Technician | 0% | 2025-08-11 | 2025-08-20 | bar: 11 month 1 to 11 month 2
1.8.3 | Bug Fixes | Maintenance Engineer | 0% | 2025-08-21 | 2025-09-10 | bar: 11 month 3 to 12 month 1
1.8.4 | Summarize Project Outcomes | Business Analyst | 0% | 2025-09-11 | 2025-09-18 | bar: 12 month 2
M 8.2 | Final Project Report Delivered |  | Scheduled |  | 2025-09-19 | bar: 12 month 3

## Milestones
Phase | ID | Name | Date | Description | Status
Project Initiation | M 1.1 | Project Kickoff | 2024-11-01 | Formal start of the project with stakeholder alignment on goals, budget, and timeline | Complete
| M 1.2 | Project Charter Approved | 2024-10-15 | Approval of the project charter, confirming scope, objectives, and resource allocation | Complete
Requirements Gathering | M 2.1 | Requirements Document Approved | 2024-11-21 | Formal approval of the software and hardware requirements specification | Complete
| M 2.2 | Blueprint and design approved | 2024-12-04 | Formal approval of the blueprint and design | Complete
| M 2.3 | System Architecture Finalized | 2024-12-12 | Completion of the high-level system design, including hardware-software integration plans | Complete
Software Development | M 3.1 | Software Development Complete | 2024-12-27 | Completion of software module coding, including navigation, obstacle detection, and control systems | On Track
| M 3.2 | Quality assurance of the software | 2025-01-29 | Completion of the code reviews and debugging, versions control and documentation | Scheduled
Hardware Development | M 4.1 | Hardware Prototype Ready | 2025-01-16 | A functional prototype of the drone, including integrated hardware components, ready for testing | On Track
| M 4.2 | Functionality Evaluated | 2025-03-21 | Battery life and power consumption evaluated, Sensors, Cameras and Actuators are integrated and ready for assembly | Scheduled
| M 4.3 | Performance Optimized | 2025-03-25 | Design and functions optimized and ready for testing | Scheduled
Testing | M 5.1 | Unit Testing Complete | 2025-04-10 | Verification of individual software modules and hardware components | Scheduled
| M 5.2 | Integration Testing Complete | 2025-04-17 | Validation of integrated hardware and software systems | Scheduled
| M 5.3 | Performance Testing Complete | 2025-04-17 | Successful flight tests, including range, obstacle detection, and payload management testing | Scheduled
| M 5.4 | Security Testing Complete | 2025-04-17 | Validation of security software | Scheduled
| M 5.5 | Testing Complete | 2025-04-21 | Full system verification, ensuring readiness for deployment and manufacture | Scheduled
Manufacture | M 6.1 | Manufacturing Workflow Established | 2025-04-08 | Finalization of manufacturing workflows, including resource and logistics planning | Scheduled
| M 6.2 | Completion of education | 2025-04-28 | First butch of workers educated and ready to work | Scheduled
| M 6.3 | Manufacture Complete | 2025-06-25 | Completion of full-scale production of drones as per project requirements | Scheduled
Deployment | M 7.1 | Deployment Plan Finalized | 2025-07-23 | Confirmation of deployment strategy, resources, and timelines | Scheduled
| M 7.2 | Manuals and guides prepared | 2024-12-15 | Completion of the manuals and guides for drone and app usage | Scheduled
| M 7.3 | System Deployed to End Users | 2025-08-12 | Successful deployment of drones and related systems to intended users | Scheduled
Post-deployment | M 8.1 | Continuous Improvement Plan Established | 2025-08-19 | Completion of the schedule for maintenance | Scheduled
| M 8.2 | Final Project Report Delivered | 2025-09-19 | Completion of the bug fixes and summarization of the first launch of the product | Scheduled

## Risk Matrix
Risk Assessment | [6 empty] | Impact Probability | Unlikely | Rare | Possible | Likely | Certain | Probability | Unlikely
Date Last Updated: |  | 14.12.2024 |  |  |  |  | Very low | 1 | 2 | 3 | 4 | 5 | Impact | High
|  |  |  | Risk Matrix |  |  | Low | 2 | 4 | 6 | 8 | 10 | Score | 4
Risk ID | Risk | Risk Descriprion | Strategy | Impact | Probability | Score | Medium | 3 | 6 | 9 | 12 | 15
1 | Technology Challenges | Integration issues between hardware and software components | Perform early proof-of-concept testing for challenging technologies. Involve technical experts and consultants to address complex integration challenges | High | Possible | 12 | High | 4 | 8 | 12 | 16 | 20
2 | Cybersecurity Threats | Potential vulnerabilities in drone systems that could lead to data breaches or hijacking | Implement encryption protocols and firewalls to secure systems. Conduct regular penetration testing (white hacking) and cybersecurity audit | Very high | Possible | 15 | Very high | 5 | 10 | 15 | 20 | 25
3 | Performance Issues | Failure to meet speed, stability, or payload capacity expectations during testing | Conduct rigorous stress testing and performance benchmarks during development. Build a modular design that allows for scalable performance improvements | Medium | Likely | 12
4 | Resource Shortages | Unavailability of skilled personnel, raw materials, or critical components | Establish strong vendor agreements with flexibility for unexpected shortages | High | Unlikely | 3
5 | Key Personnel Dependency | Loss of critical team members impacting project continuity | Identify critical personnel and document their knowledge in shared repositories. Develop succession plans and assign secondary team members for essential roles | Medium | Possible | 9
6 | Delays | Missed deadlines due to unforeseen challenges in design, manufacturing, or testing | Monitor project progress closely using milestone tracking and dashboards. Prepare a contingency plan to redistribute tasks or reallocate resources in case of delays | High | Likely | 16
7 | Testing Overruns | Extended testing cycles caused by recurring system failures | Automate repetitive test cases using testing tools. Allocate dedicated resources for both manual and automated testing to avoid bottlenecks | Low | Rare | 4
8 | Budget Overruns | Increased costs due to scope changes or unforeseen technical challenges | Regularly review and adjust budgets in response to project changes. Identify cost-saving opportunities, such as outsourcing non-critical task | Medium | Possible | 9
9 | Vendor Cost Fluctuations | Unexpected price increases for components or services | Negotiate fixed-price contracts with key vendors to minimize unpredictability. Track market trends to anticipate and mitigate price fluctuations | Medium | Likely | 12
10 | Geopolitical Factors | International trade tensions or conflicts affecting supply chain reliability | Diversify suppliers geographically to reduce dependency on politically volatile regions. Maintain an inventory buffer for critical components | Low | Likely | 8
11 | Competition | Emergence of more advanced or cost-effective solutions from competitors | Continuously monitor competitors’ products and market strategies. Emphasize unique selling points and innovation in project deliverables | Medium | Certain | 15
12 | Manufacturing Defects | Errors during production impacting quality or functionality | Implement strict quality control measures and inspections during production. Establish a feedback loop between production teams and design engineers | High | Rare | 8

## Funds
Project Budget
Total
[9 empty] | BUDGET | ACTUAL | Under(Over) | Contingency fund
[9 empty] | 500000 | 21878 | 478122 | 50000
|  | Labor |  | Materials |  | Fixed Costs
WBS | Task | Hrs | Rate | Units | $/Unit | Procurement | Travel | Other | Budget | Actual | Under(Over)
1.1 | Project Initiation | 284 | 200 | [5 empty] | 10000 | 8590 | 1410
1.1.1 | Define Project Scope | 28 | 15 | 0 | 0 | 20 | 0 | 60 | 500 | 700 | -200
1.1.2 | Stakeholder Identification | 28 | 30 | 0 | 0 | 0 | 500 | 160 | 1500 | 1243 | 257
1.1.3 | Develop Project Charter | 56 | 15 | 0 | 0 | 100 | 0 | 60 | 1000 | 659 | 341
1.1.4 | Assemble Project Team | 56 | 20 | 0 | 0 | 0 | 280 | 600 | 2000 | 1900 | 100
1.1.5 | Market Research | 56 | 35 | 0 | 0 | 300 | 0 | 240 | 2500 | 1769 | 731
1.1.6 | Risk managment Plan | 20 | 35 | 0 | 0 | 0 | 0 | 300 | 1000 | 955 | 45
1.1.7 | Plan Budget | 20 | 35 | 0 | 0 | 200 | 0 | 100 | 1000 | 865 | 135
1.1.8 | Plan Schedule | 20 | 15 | 0 | 0 | 50 | 0 | 150 | 500 | 499 | 1
1.2 | [ Level 1 Category ] | [7 empty] | 30000 | 13288 | 16712
1.2.1 | Sofware Requirements Specification | 112 | 50 | 5 | 100 | 300 | 0 | 600 | 7000 | 5688 | 1312
1.2.2 | Hardware Requirements Specification | 112 | 60 | 5 | 60 | 380 | 0 | 600 | 8000 | 7600 | 400
1.2.3 | Regulatory and Compliance Documentation | 56 | 70 | 0 | 0 | 390 | 140 | 510 | 3000 | 0 | 3000
1.2.3.1 | Identify Regulatory Standards | 14 | 35 | 0 | 0 | 200 | 140 | 170 | 1000 | 800 | 200
1.2.3.2 | Gap Analysis | 42 | 35 | 0 | 0 | 190 | 0 | 340 | 2000 | 2300 | -300
1.2.4 | Design | 168 | 150 | 10 | 20 | 600 | 240 | 1580 | 12000 | 0 | 12000
1.2.4.1 | Blueprints | 84 | 55 | 0 | 0 | 300 | 0 | 580 | 5500 | 4700 | 800
1.2.4.2 | Prototype Validation | 28 | 20 | 0 | 0 | 0 | 240 | 200 | 1000 | 700 | 300
1.2.4.3 | Software Algorithm Design | 56 | 75 | 10 | 20 | 300 | 0 | 800 | 5500 | 4600 | 900
1.3 | [ Level 1 Category ] | [7 empty] | 120000 | 0 | 120000
1.3.1 | Development of Core Features | 784 | 1022 | 3 | 60 | 550 | 0 | 3206 | 110000 | 0 | 110000
1.3.1.1 | Autonomous Navigation Algorithms | 168 | 115 | 0 | 0 | 80 | 0 | 600 | 20000 | 0 | 20000
1.3.1.2 | Obstacle Detection and Avoidance | 168 | 115 | 0 | 0 | 80 | 0 | 600 | 20000 | 0 | 20000
1.3.1.3 | Communication Systems Development | 112 | 130 | 3 | 60 | 20 | 0 | 240 | 15000 | 0 | 15000
1.3.1.4 | Develop Real-time Communication Protocols | 112 | 142 | 0 | 0 | 0 | 0 | 96 | 16000 | 0 | 16000
1.3.1.5 | UI/UX Design | 56 | 130 | 0 | 0 | 50 | 0 | 670 | 8000 | 0 | 8000
1.3.1.6 | Implement Security Measures Against Hacking | 112 | 140 | 0 | 0 | 20 | 0 | 300 | 16000 | 0 | 16000
1.3.1.7 | Data Encryption for Communication | 56 | 250 | 0 | 0 | 300 | 0 | 700 | 15000 | 0 | 15000
1.3.2 | Quality Assurance | 168 | 110 | 0 | 0 | 50 | 0 | 430 | 10000 | 0 | 10000
1.3.2.1 | Code Reviews and Debugging | 112 | 60 | 0 | 0 | 0 | 0 | 280 | 7000 | 0 | 7000
1.3.2.2 | Version Control and Documentation | 56 | 50 | 0 | 0 | 50 | 0 | 150 | 3000 | 0 | 3000
1.4 | Hardware Development | [7 empty] | 140000 | 0 | 140000
1.4.1 | Build Initial Drone Body Prototype | 264 | 80 | 10 | 150 | 30 | 0 | 350 | 23000 | 0 | 23000
1.4.2 | Hardware Component Testing | 224 | 85 | 0 | 0 | 380 | 0 | 580 | 20000 | 0 | 20000
1.4.3 | Integrate Sensors, Cameras and Actuators | 240 | 120 | 20 | 350 | 400 | 0 | 800 | 37000 | 0 | 37000
1.4.4 | Evaluate Battery Life and Power Consuption | 168 | 120 | 20 | 200 | 140 | 0 | 700 | 25000 | 0 | 25000
1.4.5 | Performance Optimization | 224 | 270 | 20 | 250 | 300 | 0 | 1960 | 35000 | 0 | 35000
1.4.5.1 | Refine Aerodynamic Design | 112 | 150 | 10 | 150 | 200 | 0 | 1500 | 20000 | 0 | 20000
1.4.5.2 | Optimize Weight for Maximum Efficiency | 112 | 120 | 10 | 100 | 100 | 0 | 460 | 15000 | 0 | 15000
1.5 | Testing | [7 empty] | 30000 | 0 | 30000
1.5.1 | Unit Testing | 224 | 85 | 0 | 0 | 270 | 0 | 370 | 10000 | 0 | 10000
1.5.1.1 | Test Individual Software Modules | 144 | 40 | 0 | 0 | 70 | 0 | 170 | 6000 | 0 | 6000
1.5.1.2 | Verify Hardware Components | 80 | 45 | 0 | 0 | 200 | 0 | 200 | 4000 | 0 | 4000
1.5.2 | Integration Testing | 192 | 35 | 0 | 0 | 58 | 0 | 222 | 7000 | 0 | 7000
1.5.3 | Performance Testing | 200 | 31 | 0 | 0 | 50 | 350 | 400 | 7000 | 0 | 7000
1.5.4 | Security Testing | 224 | 26 | 0 | 0 | 50 | 0 | 126 | 6000 | 0 | 6000
1.6 | Manufacturing | [7 empty] | 114000 | 0 | 114000
1.6.1 | Supply Chain Managment | 168 | 160 | 0 | 0 | 200 | 900 | 460 | 15000 | 0 | 15000
1.6.1.1 | Source Required Materials and Components | 140 | 80 | 0 | 0 | 100 | 600 | 100 | 12000 | 0 | 12000
1.6.1.2 | Verify Supplier Quality Standards | 28 | 80 | 0 | 0 | 100 | 300 | 360 | 3000 | 0 | 3000
1.6.2 | Production Process Setup | 336 | 190 | 40 | 10 | 5160 | 1440 | 10000 | 45000 | 0 | 45000
1.6.2.1 | Establish Manufacturing Lines | 112 | 130 | 0 | 0 | 5000 | 440 | 10000 | 30000 | 0 | 30000
1.6.2.2 | Educate Factory Workers on Assembly Procedures | 224 | 60 | 40 | 10 | 160 | 1000 | 0 | 15000 | 0 | 15000
1.6.3 | Drone Assembly | 336 | 350 | 0 | 0 | 2200 | 0 | 960 | 39000 | 0 | 39000
1.6.3.1 | Assemble Drone Bodies | 168 | 90 | 0 | 0 | 800 | 0 | 80 | 16000 | 0 | 16000
1.6.3.2 | Assemble Drone Remote Controls | 112 | 110 | 0 | 0 | 1000 | 0 | 680 | 14000 | 0 | 14000
1.6.3.3 | Install Software and Hardware Components | 56 | 150 | 0 | 0 | 400 | 0 | 200 | 9000 | 0 | 9000
1.6.4 | Approve Units for Deployment | 168 | 85 | 0 | 0 | 400 | 0 | 320 | 15000 | 0 | 15000
1.7 | Deployment | [7 empty] | 36000 | 0 | 36000
1.7.1 | Deployment Planning | 168 | 97 | 0 | 0 | 184 | 400 | 400 | 10000 | 0 | 10000
1.7.1.1 | Define Deployment Strategy | 56 | 33 | 0 | 0 | 52 | 0 | 100 | 2000 | 0 | 2000
1.7.1.2 | Allocate Deployment Resources | 112 | 64 | 0 | 0 | 132 | 400 | 300 | 8000 | 0 | 8000
1.7.2 | Install Final Software and Hardware | 112 | 135 | 0 | 0 | 380 | 0 | 500 | 16000 | 0 | 16000
1.7.3 | Prepare Maintenance and Support Manuals | 112 | 40 | 0 | 0 | 380 | 0 | 140 | 5000 | 0 | 5000
1.7.4 | Open Drones for Sale | 112 | 38 | 0 | 0 | 0 | 0 | 744 | 5000 | 0 | 5000
1.8 | Post-deployment | [7 empty] | 20000 | 0 | 20000
1.8.1 | Schedule Regular Maintenance | 56 | 35 | 0 | 0 | 0 | 0 | 40 | 2000 | 0 | 2000
1.8.2 | Collect User Feedback | 84 | 55 | 0 | 0 | 0 | 0 | 380 | 5000 | 0 | 5000
1.8.3 | Bug Fixes | 140 | 70 | 0 | 0 | 100 | 0 | 100 | 10000 | 0 | 10000
1.8.4 | Summarize Project Outcomes | 56 | 50 | 0 | 0 | 0 | 0 | 200 | 3000 | 0 | 3000
.