## Ark1
CR Ref. | CR Date | Approved By | Approval Date | Analyzed By | Analysis Start Date | Analysis End Date | Implemented By | Emplementation Start Date | Implementation End Date | Peer Review By | Peer Review Start Date | Peer Review End Date | Tested By | Testing Start Date | Testing End Date | Status | Closed Date
1.2 | 2023-12-01 | Ihor Khoroshun | 2023-12-01 | Daniil Arbatov | 2023-12-01 | 2023-12-01 |  |  |  | Hanna Asiadouskaya | 2023-12-01 | 2023-12-01 |  |  |  | Rejected | 2023-12-01
1.5/2.2 | 2023-12-01 | Ihor Khoroshun | 2023-12-02 | Ivan Kapusta | 2023-12-02 | 2023-12-02 | Ivan Kapusta | 2023-12-02 | 2023-12-05 | Hanna Asiadouskaya | 2023-12-02 | 2023-12-05 | Ivan Kapusta | 2023-12-05 | 2023-12-05 | Accept | 2023-12-02
2.1 | 2023-12-01 | Ihor Khoroshun | 2023-12-03 | Artem Shymko | 2023-12-03 | 2023-12-03 | Artem Shymko | 2023-12-03 | 2023-12-03 | Hanna Asiadouskaya | 2023-12-03 | 2023-12-02 | Artem Shymko | 2023-12-03 | 2023-12-03 | Accept | 2023-12-03